## Slide 1: Transitioning to Agile: Lessons learned from SNHU Travel
Jeri Mabuti
July 1, 2024

## Slide 2: Introduction to Agile
Agile methodology emphasizes flexibility, iterative development, and continuous feedback, allowing teams to adapt quickly to changes and deliver incremental value to stakeholders.
Project Overview
The SNHU Travel project aimed to develop an innovative travel booking tool using the Agile methodology as a pilot for ChadaTech.

## Slide 3: Agile Roles
Scrum Master: Facilitates the Scrum process and ensures team efficiency.
  Organized daily stand-ups, sprint planning, and retrospectives, ensuring clear communication and continuous improvement (Portman, 2022)​.
Product Owner: Represents user needs and prioritizes the backlog.
  Engaged with stakeholders to refine user stories and prioritize tasks based on business value (Ghiba, 2022).
Developer: Implements user stories into working software.
  Developed features based on prioritized backlog items and ensured alignment with user stories (Unger et al., 2021)​
Tester: Ensures the software meets acceptance criteria.
  Created and executed comprehensive test cases to validate functionality and identify issues (Rush & Connolly, 2020)​

## Slide 4: Agile Phases and Their Importance
Sprint Planning
  Define goals and prioritize tasks for the sprint.
  Importance: Sets clear objectives and ensures the team is aligned on priorities.
Daily Standups
  Short, daily meetings to discuss progress and identify obstacles.
  Importance: Keeps the team aligned and proactive in addressing issues, ensuring continuous progress (Overeem, 2016)
Sprint Review
  Demonstrate completed work and gather feedback.
  Importance: Provides an opportunity for stakeholder feedback and validation of progress (Schwaber & Sutherland, 2020)
Sprint Retrospective
  Reflect on the sprint and identify areas for improvement.
  Importance: Facilitates continuous improvement and helps the team learn from their experiences (Yela Aránega et al., 2023)

## Slide 5: The Waterfall model
Overview:
  Sequential phases with clear milestones and deliverables.
  Pros: Structured approach, easier to manage fixed budgets and timelines.
  Cons: Inflexible to changes, delayed feedback until project completion.
If our team had used the Waterfall approach:
  Handling the shift from "Top 5 Destinations" to "Top 5 Detox/Wellness Destinations" would have been challenging
    Due to the rigid structure and lack of iterative feedback.

## Slide 6: Waterfall vs. agile: pros and cons
 | Pros | Cons
Agile | Flexibility, continuous feedback, quick adaptation to changes (Gandomani et al., 2020). | Requires constant communication, potential for scope creep.
Waterfall | Clear structure, predictable timelines. | Rigid, less responsive to changes.

## Slide 7: Factors to consider when choosing an approach
Project Complexity:
  Agile is better for complex, dynamic projects with evolving requirements.
Stakeholder Engagement:
  Agile requires active participation from stakeholders for continuous feedback.
Flexibility Needs:
  Agile allows for adjustments and changes throughout the project, making it suitable for projects with uncertain or evolving requirements.
Example from SNHU Travel Project:
  The flexibility of Agile allowed us to adapt to the client's request to shift focus from general destinations to detox/wellness travel, ensuring the project remained aligned with stakeholder needs.

## Slide 8: Tools and Communication in Agile
Tools Used:
JIRA: For task tracking and collaboration.
Smartsheet: For progress monitoring and project management.
Importance of Communication:
Daily stand-ups and tools like JIRA and Slack facilitate clear and timely communication.
  Ex. Having detailed email communications ensured clarity and alignment on project goals (Portman, 2022)​
Effectiveness:
These tools and communication practices helped us manage tasks efficiently and adapt to changes smoothly (Spagnoletti et al., 2022)​
When the sudden change from "Top 5 Destinations" to "Top 5 Wellness/Detox" occurred, we used emails to communicate this shift effectively to all team members, ensuring everyone was on the same page and could adjust their work accordingly.

## Slide 9: Lessons Learned from snhu travel project
Applying Roles:
  Each role contributed significantly: Scrum Master facilitated processes, Product Owner prioritized backlog, Developer implemented features, Tester ensured quality.
Completing User Stories:
  The iterative development approach helped us complete user stories effectively. For example, the story "As a cost-conscious user, I want to set a price limit..." was developed and tested iteratively (Ghiba, 2022)​
Handling Interruptions:
  Agile's flexibility allowed us to handle the shift to a detox/wellness travel focus efficiently.
Communication:
  Effective use of meetings and tools like JIRA and Slack ensured continuous alignment and progress (Portman, 2022)

## Slide 10: Conclusion and Recommendations

## Slide 11: Summary: Benefits of Using Agile
Flexibility:
  Agile allowed us to adapt quickly to changing requirements. For instance, when the client requested a shift from "Top 5 Destinations" to "Top 5 Wellness/Detox Destinations," we were able to make the necessary adjustments without significant delays.
Continuous Feedback:
  Regular Sprint Reviews and Retrospectives facilitated continuous feedback from stakeholders, ensuring the project remained aligned with client expectations.
Improved Collaboration:
  Daily stand-ups and effective communication tools like JIRA and Slack enhanced team collaboration and kept everyone on the same page.
Iterative Development:
  Breaking down the project into manageable sprints allowed us to deliver incremental value, keeping the project on track and making it easier to manage and adapt to changes.

## Slide 12: Summary: Challenges of Using Agile
Constant Communication Needs:
  Agile requires regular communication and coordination, which can be time-consuming and may initially slow down the process as the team adapts.
Managing Scope Creep:
  The flexibility of Agile can sometimes lead to scope creep, where additional features are added beyond the initial plan, requiring careful management and prioritization.
Learning Curve:
  Transitioning from a Waterfall to an Agile methodology involves a learning curve for team members, who must adapt to new processes and tools.

## Slide 13: Recommendation: project success using agile
Flexibility and Responsiveness:
  The ability to swiftly adapt to the client's changing requirements was a significant success factor. When the client shifted the focus from "Top 5 Destinations" to "Top 5 Wellness/Detox Destinations," Agile allowed us to incorporate these changes smoothly and efficiently.
Client Satisfaction:
  Continuous feedback loops through Sprint Reviews ensured that the client's needs and expectations were consistently met, resulting in high client satisfaction.
Team Cohesion:
  The use of Agile fostered a collaborative team environment. Regular communication and iterative development practices helped build a cohesive team that worked well together, leading to a successful project outcome.
Delivering Value Incrementally:
  By delivering the project in iterations, we could show tangible progress at the end of each sprint, keeping the client engaged and confident in the project's direction.

## Slide 14: Thank you

## Slide 15: References: Ghiba, A. C. (2022). The Product Owner Role in a Contemporary Agile Team. Annals of the University Dunarea de Jos of Galati: Fascicle: I, Economics & Applied Informatics, 28(1), 78–81. https://doi-org.ezproxy.snhu.edu/10.35219/eai15840409248 Portman, H. (2022). The ideal scrum master. PM World Journal, 11(5), 1–7. Schwaber, K., & Sutherland, J. (2020). The 2020 Scrum Guide. Scrum Guide | Scrum Guides. https://scrumguides.org/scrum-guide.html Rush, D. E., & Connolly, A. J. (2020). An Agile Framework for Teaching with Scrum in the IT Project Management Classroom. Journal of Information Systems Education, 31(3), 196–207. Gandomani, T. J., Tavakoli, Z., Zulzalil, H., & Farsani, H. K. (2020). The Role of Project Manager in Agile Software Teams: A Systematic Literature Review. IEEE Access, Access, IEEE, 8, 117109-117121. https://doi-org.ezproxy.snhu.edu/10.1109/ACCESS.2020.3004450 Yela Aránega, A., Castaño Urueña, R., Castaño Sánchez, R., & Gonzalo Montesinos, C. (2023). Agile methodologies and emotional intelligence: An innovative approach to team management. Journal of Competitiveness, 15(3), 164 183. https://doi-org.ezproxy.snhu.edu/10.7441/joc.2023.03.09 Spagnoletti, P., Kazemargi, N., & Prencipe, A. (2022). Agile Practices and Organizational Agility in Software Ecosystems. IEEE Transactions on Engineering Management, Engineering Management, IEEE Transactions on, IEEE Trans. Eng. Manage, 69(6), 3604–3617. https://doi-org.ezproxy.snhu.edu/10.1109/TEM.2021.3110105